## Checklist
Test Plan Review Checklist
Project: | MERN Store
Release: | MERNStore v1.0
Reviewers | Tester / Developer / Project Manager
Document: | 4_Test_Plan_Review_Checklist.xlsx)
Date: | 2025-12-16
Document ID: | TPRC-MERNSTORE-01
Template Used: | Test Plan Review Checklist.xls 1.0
No. | Criteria | Yes/No/NA | Remarks
A | OVERVIEW
1 | Does the test plan template conform to the specified standards/guidelines? | Yes | Conforms to template; see document control.
2 | Can the boundaries or scope of the test be clearly identified? | Yes | Scope clearly defined in In/Out of scope section.
3 | Are all prerequisites and other related documents identified? | Yes | Prerequisites & references listed.
4 | Is the test traceable to requirement(s)? | Yes | Traceability matrix provided.
5 | Is the test plan under version control? | Yes | Version/revision info provided.
B | CONTENT
1 | Does the Test Plan address the following required information clearly? | Yes | All required sections are covered in Combined sheets.
2 | Test Objectives | Yes | Test objectives stated under Purpose.
3 | Test Scope | Yes | Test scope defined (In/Out of scope).
4 | Test Strategy | Yes | Strategy described (levels/types/approaches).
5 | Resources (such as material, tools and human) | Yes | Resources and roles documented.
6 | Test Schedule | Yes | Schedule and milestones documented.
7 | Test Environment | Yes | Environment & configuration documented.
8 | Test Deliverables | Yes | Deliverables documented.
9 | Test Reporting | Yes | Reporting/defect tracking documented.
10 | Does the test plan identify the essential team member roles & responsibilities? | Yes | Roles & responsibilities identified.
11 | Does the plan include detailed specifications, descriptions, and procedures for testing all systems? | Yes | Procedures/coverage by module and traceability provided.
12 | Does the document describe the type(s) of tests to be addressed? | Yes | Test types described.
13 | For the test type, does the document list all relevant tests necessary to be applied to the chosen part of the system? | Yes | Approach/techniques defined per test types.
14 | Are integration tests included? | Yes | Integration tests included in strategy and coverage.
15 | Is the test coverage sufficient? | Yes | Coverage matrix by module/scenario included.
16 | Is the schedule within a currently agreed time frame? | Yes | Schedule aligned with project timeline.
17 | Are the testing dependencies (if any) addressed? | Yes | Assumptions/dependencies captured.
18 | Has the entrance criteria for the testing activities been identified? | Yes | Entry/readiness criteria defined.
19 | Has the exit criteria, including thresholds for performance deviation, for the testing activities been identified? Example: All severity 1 and 2 defects must be closed and approved plans for severity 3 defects are defined in the Test Report. | Yes | Exit/stop/success thresholds defined.
20 | Has a regression strategy been defined for regression testing when changes or enhancements in system design occur? | Yes | Regression strategy defined.

## Checklist_Index
No. | Test Plan Section (Word) | Target Sheet | Sheet Purpose / What to Review | Status (Yes/No/NA) | Go to sheet
1 | Document Control | Doc Control | Thông tin tài liệu, người soạn/review/approve, version/revision history | No | Go | Status = No → đúng yêu cầu “đang chờ review/fix”
2 | 3.1 Introduction | TestPlan_Scope_Strategy | Purpose, background, scope (in/out), assumptions, constraints, references, training needs | No | Go
3 | 3.1 Risks | TestPlan_Risks | Risk register: ID, risk, impact/likelihood, mitigation/contingency | No | Go
4 | 3.2 Work products | TestPlan_Coverage_By_Module | Danh sách module/feature under test + coverage theo module | No | Go
5 | 3.2 Traceability | TestPlan_Traceability | Mapping requirements/use cases/routes ↔ test cases (traceability matrix) | No | Go
6 | 3.4 Test strategy | TestPlan_TestTypes | Test levels/types, approaches, automation vs manual, tools usage | No | Go
7 | 3.4 Entry/Exit | TestPlan_Entry_Exit_Criteria | Readiness/stop/success/regression criteria | No | Go
8 | 3.5 Environment | TestPlan_Environment | HW/SW versions, configurations, browsers, environment setup (Docker/staging) | No | Go
9 | 3.5 Resources | TestPlan_Resources | Roles & responsibilities, staffing, responsibilities matrix | No | Go
10 | 3.6 Schedule | TestPlan_Schedule_Milestones | Testing phases, timeline, milestones and deadlines | No | Go
11 | 3.7 Reporting | TestPlan_Reporting | Communication channels, defect tracking process, reporting cadence | No | Go
12 | 3.8 Deliverables | TestPlan_Deliverables | Test artefacts to deliver: test cases, logs, defect report, summary report | No | Go
13 | (Ref) Document control table | TestPlan_DocumentControl | Bảng Document Control (nếu tách riêng) | No | Go

## Doc Control
This information is for template control purpose only. This page can be removed when an actual document is made.
Document Control Page
Test Plan Review Checklist |  | 4_Test_Plan_Review_Checklist.xlsx)
Template version: | 1.1
Template status: | Approved
Template file name: | Test Plan Review Checklist.xls
Template document ID | CK-PP-091002
Revision history of this template
Version No. | Revision Date | Change Description | Author's Name | Approver's Name | Approver's Title
0.8 | 2009-09-25 | Draft | Duc, Chau Man
0.9 | 2009-12-09 | Reviewed, corrected | Du Chu
1.0 | 2010-01-04 | Approved |  | Hy Thai | DE Manager
1.02 | 2011-01-26 | Remove A1, B1, B2, B3, B4, B5, C12, C13, D1, D2, D3, D5, D6, D7, D8, D9, D12, D13, D14 Add C15 -> 19 (before removal) | Tien Tran
1.05 | 2011-02-14 | Add 2 checkpoints about entrance criteria and exit criteria based on OPAL Detailed Test Plan | Tien Tran
1.1 | 2011-02-15 | Approved | Tien Tran | Tien DD | SEPG Head
Usage notes:
Use this template to develop the various kinds of documents. The content of the document are subjected to be filled and changed in the document, according to the following legends:
Blue comment: The brief guidance on how to fill the sections. These parts shall be removed from the actual documents.
Example (Red text): The brief example to illustrate the sections. These parts shall be removed from the actual documents.
[Text in brackets]: Shall be replaced with the actual contents.

## TestPlan_Coverage_By_Module
Module | Key Scenarios | Priority
Authentication | Login valid/invalid; Register unique email; Forgot/Reset; Social callback success/failure | P0
User Profile | View/update own profile; non‑auth blocked | P1
Address | Add/list own; invalid phone/zipcode; (BUG) edit/delete/get by id without auth (negative) | P0
Catalog | List with sort/filter; category/brand active only; search name suggestions | P0
Product Detail | Slug not found/brand inactive → 404; correct fields and image substitute | P0
Wishlist | Add/remove; duplicate; non‑auth/admin blocked; invalid ObjectId | P1
Cart | Create cart; add/remove item; increase/decrease qty; qty bounds; admin blocked; stock adjust | P0
Checkout/Order | Submit with address+payment; history/detail; complete ready/not ready; cancel edge cases | P0
Reviews | Post allowed only after Delivered/Completed; moderation paths; duplicate; approve/reject/delete auth | P1
Newsletter | Subscribe valid/duplicate/invalid email | P2
Contact | Add request required fields; duplicate email | P2
Brand/Category | Active lists; select endpoints; disable brand cascades | P2
Dashboard | Admin summary with revenue/orders/pending/topProducts | P1
Health | /health returns 200 | P2
Module | Covered Scenarios | Test Types | Priority | Notes | Bảng ghi chú
Authentication | Login valid/invalid; Register; Forgot/Reset; Social callbacks; Reset khi đã login cần JWT | Functional / Security | P0 | Entry point of system | P0 | Critical: Ảnh hưởng trực tiếp business / bảo mật/ P0 FAIL = không được triển khai
User Profile | View/update own profile; non-auth blocked | Functional / Security | P1 | JWT & ownership | P1 | Important: Không chết hệ thống nhưng ảnh hưởng trải nghiệm / kiểm soát
Address | Add/list own; invalid phone/zipcode | Functional / Validation | P0 | User private data | P2 | Nice-to-have: Phụ trợ
Address (Negative) | GET/PUT/DELETE by id without owner check | Security / Negative | P0 | Auth gap (BUG)
Catalog | List with sort/filter; category/brand active only; search suggestions | Functional / API | P0 | Core browse flow
Product Detail | Slug not found; brand inactive → 404; image fallback | Functional / Negative | P0 | Data integrity
Wishlist | Add/remove; duplicate; non-auth/admin blocked; invalid ObjectId | Functional / Security | P1 | Non-core feature
Cart | Create cart; add/remove item; qty bounds; admin blocked; stock adjust | Functional / Security | P0 | Affects order correctness
Orders | Create; history; detail; complete/cancel | Functional / API | P0 | Core business flow
Orders (Negative) | Non-admin GET /order leak; /order/add tin total client; Checkout không kiểm stock | Security / Negative | P0 | Known gaps in code
Reviews | Review only after Delivered/Completed | Functional / Negative | P1 | Moderation logic
Reviews (Moderation) | Approve/reject/delete review | Security / Negative | P1 | Role-check missing
Newsletter | Subscribe valid/duplicate/invalid email | Functional | P2 | Auxiliary feature
Contact | Add request; required fields; duplicate email | Functional | P2 | Auxiliary feature
Brand/Category | Active lists; select endpoints; disable brand cascades | Functional / API | P2 | Config data
Dashboard | Admin summary (revenue/orders/pending/topProducts) | Functional / Security | P1 | Admin-only
Support Chat | SocketProvider disabled connect (expected) | UI / Manual | P2 | FE only
Support Chat (Security) | Bearer token required for handshake | Security | P1 | No realtime execution
Health | /health returns 200 | Smoke Test | P2 | System alive check
Module | Covered Scenarios | Test Types | Priority | Notes
Authentication | Login valid/invalid; Register; Forgot/Reset; JWT & role checks | Functional / Security | P0 | Entry & access control
Catalog / Search | List with filter/sort; search by name; product detail correctness | Functional / API | P0 | Core browse flow
Cart | Create cart; add/remove items; qty bounds; admin blocked; stock adjust | Functional / Security | P0 | Impacts order correctness
Orders | Create order; history; detail; complete/cancel | Functional / API | P0 | Core business flow
Orders (Negative) | Order leak; tampering total; missing stock check; status update without role | Security / Negative | P0 | Known gaps in code
Address (Minimal) | Use seeded address for checkout; ownership/auth if applicable | Functional / Security | P1 | Minimal dependency

## TestPlan_Deliverables
Deliverable | Owner | Format
Approved Test Plan | QA/PM | MD + CSV (importable to Excel)
Test Cases | QA | Markdown/CSV (linked to endpoints)
Test Data | QA | CSV/JSON seed
Execution Evidence | QA | Screenshots/Logs
Daily/Final Test Report | QA | MD/PDF with metrics
Defect Log | QA | Jira/Sheet with details

## TestPlan_DocumentControl
Field | Value
Project | MERN Store
Project Code | MERN-STORE
Document | Test Plan
Document Code | TP-MERN-STORE-v1.0
Version | 1.0
Status | Final
Issue Date | 2025-12-16
Prepared By | Project Team
Reviewed By | Project Manager
Approved By | Stakeholders / Instructor
Change Log | v1.0 Initial plan from current codebase

## TestPlan_Entry_Exit_Criteria
Category | Criteria
Entry | Code freeze for tested scope
Entry | Environment up and reachable
Entry | Seed data prepared and accounts created
Entry | Test Plan approved; test design ≥95%
Exit | All P0/P1 defects closed
Exit | P2 defects have accepted workaround or fix plan
Exit | Critical scenario pass rate ≥95%
Exit | Reports and evidence published; stakeholders sign‑off

## TestPlan_Environment
Category | Details
Hardware | QA workstation (8GB+ RAM)
OS | Windows/macOS/Linux supported by dev env
Runtime | Node.js LTS (per server/package.json) | npm
Database | MongoDB (local or container)
Browsers | Chrome/Firefox latest; Safari/Edge optional | 4_Test_Plan_Review_Checklist.xlsx)
Network | Localhost/staging; stable internet for Mailchimp/Mailgun sandbox
Data | Seed products/brands/categories/users; test emails
Logging | Server console logs; access to error logs if available

## TestPlan_Reporting
Topic | Details | Frequency | Audience | Format | Owner
Daily Test Progress | Tiến độ, Pass/Fail, Defects mới, Blockers | Daily | QA/Dev/PM | Email/Chat/Sheet | QA
Defect Reporting | Tạo/lưu lỗi theo mẫu (mô tả, steps, expected/actual, ảnh) và phân loại mức độ | Realtime | QA/Dev | Tracker/Sheet | QA
Weekly Summary | Phủ kiểm, xu hướng lỗi, rủi ro và hành động | Weekly | PM/Stakeholders | Slide/MD | QA
Final Test Report | Tỉ lệ pass, lỗi theo mức độ/trạng thái, quyết định release, bài học kinh nghiệm | At Exit | PM/Stakeholders | PDF/MD | QA
Metrics | Pass rate, Defect density, Coverage by module, Lead time fix | Daily/Final | QA/PM | Charts in report | QA
Communication | Kênh liên lạc & thời gian cập nhật (Email/Chat/Standup) | Daily | All | Schedule note | PM

## TestPlan_Resources
Role | Name/Team | Responsibilities
QA Engineer | <Your Name> | Test design/execution/reporting | evidence
Backend Reviewer | Server Dev | API behavior & defect triage
Frontend Reviewer | Client Dev | UI behavior & defect triage
Project Manager | PM | Plan approval | scheduling | risk handling

## TestPlan_Risks
Risk | Impact | Likelihood | Mitigation
Missing role checks (order status/review moderation) | High | Medium | Add negative tests; raise bugs; quick patches before release
Address endpoints missing auth on PUT/DELETE/GET | High | High | Restrict via middleware; add owner checks; test and track
Email provider sandbox limits | Low | Medium | Stub or verify only 200 responses; avoid SLA assumptions
Insufficient seed data for flows | Medium | Medium | Prepare deterministic seed; reset DB between runs
Performance regressions on listing/search | Medium | Low | Smoke test with pagination and limits; profile queries

## TestPlan_Schedule_Milestones
Milestone | Target Date | Owner | Notes
Approve Test Plan | 2025-12-16 | PM/Approver
Complete Test Design | 2025-12-18 | QA
Start Test Execution | 2025-12-18 | QA
Cycle 1 Bug Fix/Retest | 2025-12-19 | Dev/QA
Regression Pass | 2025-12-20 | QA
Exit Review & Sign-off | 2025-12-21 | PM/QA/Dev

## TestPlan_Scope_Strategy
Section | Item | Description
In-Scope | Authentication | Login, Register, Forgot/Reset, social callbacks
In-Scope | User Profile | /user/me view + update
In-Scope | Address | Add/list own addresses; ownership & auth checks
In-Scope | Catalog | Product list with filters (price, rating, category, brand) + sort
In-Scope | Search | /product/list/search/:name suggestions
In-Scope | Product Detail | /product/item/:slug data correctness
In-Scope | Wishlist | Add/Remove/list (auth, admin blocked)
In-Scope | Cart | Create cart, add/remove items, quantity rules, stock adjust
In-Scope | Checkout/Order | Submit order with address + payment method; view history/detail; complete/cancel rules
In-Scope | Reviews | Post only for Delivered/Completed items; moderation
In-Scope | Brand/Category | Active lists and select endpoints
In-Scope | Dashboard | Admin summary (/dashboard/summary)
In-Scope | Newsletter | /newsletter/subscribe
In-Scope | Contact | /contact/add
In-Scope | Orders – Security | Negative cases: order detail leak /api/order/:id cho non-owner/non-admin
Out-of-Scope | Real Payment | Payment gateway integrations
Out-of-Scope | External Email SLA | Mail provider availability beyond sandbox
Out-of-Scope | Heavy Performance | Load/stress/volume beyond smoke
Out-of-Scope | Native Apps | Mobile native clients
Out-of-Scope | Support Chat (Realtime) | Backend realtime chat no active (UI only)
Strategy | Functional | End-to-end flows on UI and responses
Strategy | API Integration | Verify status codes, payloads, DB side effects
Strategy | Security & Access | AuthN/AuthZ/roles; owner checks
Strategy | Regression | Smoke on catalog/search/cart/order each release
Strategy | Compatibility | Chrome/Firefox latest; Safari/Edge best-effort
Strategy | Performance (smoke) | Pagination & featured/popular limits
Stages | System Test | QA executes against staging/local
Stages | UAT | Optional stakeholder verification
Entry Criteria | Readiness | Env up, data seeded, plan approved, test design ≥95%
Exit Criteria | Quality Gates | No P0/P1 open; P2 planned; pass rate ≥95% on critical
Section | Item | Description
In-Scope | Authentication / Authorization | Verify JWT authentication; role-based access control (admin/member) for protected routes
In-Scope | Catalog / Search | Product list with filter/sort (price, rating); search suggestions /product/list/search/:name
In-Scope | Cart | Create cart; add/remove items; quantity rules; stock adjust; admin blocked
In-Scope | Checkout / Order | Create order with payment & shipping; view history/detail; complete/cancel rules
In-Scope | Orders – Security | Negative cases: tampering order total; missing stock check; order detail leak /api/order/:id for non-owner/non-admin; item status update without role-check
In-Scope (Minimal) | Address | Minimal scope: use existing/seeded address for checkout; ownership/auth verified only if required
Out-of-Scope | Wishlist | Not included in narrowed test scope
Out-of-Scope | Reviews | Not included in narrowed test scope
Out-of-Scope | User Profile | Not included in narrowed test scope
Out-of-Scope | Social Callbacks | OAuth/social login flows not tested
Out-of-Scope | Support Chat | Chat feature not tested
Out-of-Scope | Newsletter | Newsletter subscribe not tested
Out-of-Scope | Contact | Contact form not tested
Out-of-Scope | Dashboard | Admin dashboard not tested
Out-of-Scope | Brand / Category UI | Brand/category management UI not tested
Out-of-Scope | Health | Health endpoint not tested
Strategy | Functional | End-to-end flows focusing on catalog → cart → checkout → order
Strategy | API Integration | Verify status codes, payloads, and DB side effects for cart/order APIs
Strategy | Security & Access | AuthN/AuthZ checks, role enforcement, ownership validation, negative testing
Strategy | Regression | Smoke regression on catalog/search/cart/order after each change
Strategy | Performance (Smoke) | Basic pagination and list limits only (no load/stress)
Stages | System Test | QA executes tests against local or staging environment
Entry Criteria | Readiness | Environment up; data seeded (products, stock, address); test plan approved
Exit Criteria | Quality Gates | No P0/P1 open in scoped modules; pass rate ≥95% on critical cart/order flows

## TestPlan_TestTypes
Type | Objective | Notes
Functional | Validate features behave as specified across key flows | UI + API checks
API Integration | Verify request/response codes, payloads and DB effects | Use Postman/REST client
Security & Access | Enforce authentication/authorization/ownership | Negative tests for missing role checks
Regression | Prevent re‑introduction of critical defects | Run smoke each release
Compatibility | Confirm basic operation on supported browsers | Chrome/Firefox latest
Performance (smoke) | Ensure listing/search/featured/popular handle nominal volume | Check pagination/limits

## TestPlan_Traceability
Area | Endpoint/Route | Key Test Criteria
Auth | /auth/login | 400 for missing fields; 400 for wrong email/pass; returns Bearer token; JWT payload contains id only
Auth | /auth/register | Unique email; hashed password; returns token; optional newsletter subscribe
Auth | /auth/forgot | /auth/reset | Reset token TTL; change password; login with new password
User | /user/me (auth) | Returns profile + role; update profile fields
User | /user (admin) | List with pagination; non‑admin blocked
Address | /address/add (auth) | Add for self; JWT required
Address | /address (auth) | List own addresses
Address | /address/:id PUT/DELETE | (BUG) missing auth/owner checks — negative tests
Product | /product/list | Filters (min/max/rating), sort fallback; category/brand filters
Product | /product/item/:slug | 404 if brand inactive/null; details correct
Product | /product/list/search/:name | 404 when none; safe for injection‑like inputs
Product | /product/featured | /product/popular | Respect limit and sort; active only
Cart | /cart/* (auth) | Purchaser gate blocks admin; create/update/delete; stock adjust
Order | /order/add (auth) | Payment method required; shipping required; address ownership
Order | /order/me | /order/:orderId | View history/detail; ownership enforced
Order | /order/complete/:orderId | Block admin; ensure all items delivered before complete
Order | /order/status/item/:itemId | (BUG) missing role‑check — negative test and defect
Wishlist | POST/GET (auth) | Admin blocked; duplicate prevent; bad product id
Review | /review/add | Only after Delivered/Completed; ownership and duplicates; approval default
Review | /review approve/reject/delete | (BUG) admin role‑check missing — negative tests
Newsletter | /newsletter/subscribe | Email required; duplicate handling
Contact | /contact/add | Required fields; duplicate email blocked
Brand/Category | /brand/list | /category/list | Active only; select endpoints
Dashboard | /dashboard/summary | Admin only; computed fields present
Health | /health | 200 OK
Requirement / Risk | Module | Endpoint / Feature | Test Type | Note
Missing / invalid login fields | Auth | POST /auth/login | Functional / Negative | 400 for missing fields; invalid email/password
Register unique email | Auth | POST /auth/register | Functional | Email unique; password hashed; token returned
Reset password flow | Auth | POST /auth/reset (JWT required when logged in) | Functional / Security | Reset token TTL; reset allowed when logged in
Social login callback | Auth | /auth/google/callback, /auth/facebook/callback | Integration | OAuth callback handling
Profile access | User | GET /user/me | Functional / Security | JWT required; returns role
Admin-only user list | User | GET /user (admin) | Security / Negative | Non-admin blocked
Add address | Address | POST /address/add | Functional | JWT required; address linked to user
Address ownership gap | Address | GET/PUT/DELETE /address/:id | Security / Negative | BUG: missing auth/owner checks
Product listing filters | Product | GET /product/list | Functional | Filter by price/rating; sort fallback
Product detail inactive brand | Product | GET /product/item/:slug | Functional / Negative | 404 if brand inactive/null
Product search safety | Product | GET /product/list/search/:name | Security | 404 when none; safe for injection-like input
Featured / popular products | Product | /product/featured, /product/popular | Functional | Active only; respect limit & sort
Cart purchaser gate | Cart | /cart/* | Security | Admin blocked by ensurePurchaser
Cart stock adjustment | Cart | POST /cart/add | Data Integrity | Stock decrease/increase correctly
Create order validation | Order | POST /order/add | Functional / Security | Payment & shipping required; address ownership
Order history access | Order | GET /order/me | Functional | View own orders only
Order detail leak | Order | GET /order/:orderId | Security / Negative | BUG: non-owner access possible
Order complete rules | Order | PUT /order/complete/:orderId | Functional / Negative | Block if not all items Delivered
Order item status role gap | Order | PUT /order/status/item/:itemId | Security / Negative | BUG: missing role-check
Tampering order total | Order | POST /order/add | Security / Validation | Server trusts client total
Missing stock check | Order | POST /order/add | Data Integrity / Negative | No stock validation before submit
Wishlist access | Wishlist | POST/GET /wishlist | Functional / Security | Admin blocked; duplicate prevented
Review allowed condition | Review | POST /review/add | Functional | Only Delivered/Completed orders
Review moderation role gap | Review | PUT /review/approve/:id | Security / Negative | BUG: missing admin role-check
Newsletter subscribe | Newsletter | POST /newsletter/subscribe | Functional | Duplicate email handling
Contact form | Contact | POST /contact/add | Functional | Required fields; duplicate blocked
Brand/category active | Brand/Category | GET /brand/list, /category/list | Functional | Active only; select endpoints
Dashboard admin summary | Dashboard | GET /dashboard/summary | Security / Functional | Admin only; computed fields present
Support chat handshake | Support Chat | Socket connect (server/socket authHandler) | Security | Bearer token required
Support chat FE disabled | Support Chat | client/app/contexts/Socket/provider.js return sớm, không connect | UI / Manual | FE renders; backend realtime disabled
Health check | Health | GET /health | Smoke Test | 200 OK
Requirement / Risk | Module | Endpoint / Feature | Test Type | Note
Login validation | Auth | POST /auth/login | Functional / Negative | Missing fields, invalid creds
Register user | Auth | POST /auth/register | Functional | Unique email, hashed password
Reset password | Auth | POST /auth/reset | Functional / Security | Token validity, reset flow
JWT & role enforcement | Auth | Protected routes | Security | Admin/member checks
Product listing | Catalog | GET /product/list | Functional | Filter/sort applied
Product search | Search | GET /product/list/search/:name | Functional | Suggestions, safe input
Product detail | Product | GET /product/item/:slug | Functional / Negative | 404 if not found
Cart operations | Cart | /cart/* | Functional / Security | Qty rules, admin blocked
Create order | Order | POST /order/add | Functional / Validation | Payment & shipping required
Order history | Order | GET /order/me | Functional | Owner only
Order detail leak | Order | GET /order/:id | Security / Negative | Non-owner access risk
Tampering order total | Order | POST /order/add | Security / Negative | Server trusts client total
Missing stock check | Order | POST /order/add | Data Integrity | No stock validation
Order status role gap | Order | PUT /order/status/* | Security / Negative | Missing role-check
Address usage (minimal) | Address | POST /address/add (seeded) | Functional | Used only for checkout