## TestPlan_Coverage_By_Module
Module | Key Scenarios | Priority
Authentication | Login valid/invalid; Register unique email; Forgot/Reset; Social callback success/failure | P0
User Profile | View/update own profile; non‑auth blocked | P1
Address | Add/list own; invalid phone/zipcode; (BUG) edit/delete/get by id without auth (negative) | P0
Catalog | List with sort/filter; category/brand active only; search name suggestions | P0
Product Detail | Slug not found/brand inactive → 404; correct fields and image substitute | P0
Wishlist | Add/remove; duplicate; non‑auth/admin blocked; invalid ObjectId | P1
Cart | Create cart; add/remove item; increase/decrease qty; qty bounds; admin blocked; stock adjust | P0
Checkout/Order | Submit with address+payment; history/detail; complete ready/not ready; cancel edge cases | P0
Reviews | Post allowed only after Delivered/Completed; moderation paths; duplicate; approve/reject/delete auth | P1
Newsletter | Subscribe valid/duplicate/invalid email | P2
Contact | Add request required fields; duplicate email | P2
Brand/Category | Active lists; select endpoints; disable brand cascades | P2
Dashboard | Admin summary with revenue/orders/pending/topProducts | P1
Health | /health returns 200 | P2

## TestPlan_Deliverables
Deliverable | Owner | Format
Approved Test Plan | QA/PM | MD + CSV (importable to Excel)
Test Cases | QA | Markdown/CSV (linked to endpoints)
Test Data | QA | CSV/JSON seed
Execution Evidence | QA | Screenshots/Logs
Daily/Final Test Report | QA | MD/PDF with metrics
Defect Log | QA | Jira/Sheet with details

## TestPlan_DocumentControl
Field | Value
Project | MERN Store
Project Code | MERN-STORE
Document | Test Plan
Document Code | TP-MERN-STORE-v1.0
Version | 1.0
Status | Draft
Issue Date | 2025-12-15
Prepared By | <Your Name>
Reviewed By | <Reviewer>
Approved By | <Approver>
Change Log | v1.0 Initial plan from current codebase

## TestPlan_Entry_Exit_Criteria
Category | Criteria
Entry | Code freeze for tested scope
Entry | Environment up and reachable
Entry | Seed data prepared and accounts created
Entry | Test Plan approved; test design ≥95%
Exit | All P0/P1 defects closed
Exit | P2 defects have accepted workaround or fix plan
Exit | Critical scenario pass rate ≥95%
Exit | Reports and evidence published; stakeholders sign‑off

## TestPlan_Environment
Category | Details
Hardware | QA workstation (8GB+ RAM)
OS | Windows/macOS/Linux supported by dev env
Runtime | Node.js LTS (per server/package.json) | npm
Database | MongoDB (local or container)
Browsers | Chrome/Firefox latest; Safari/Edge optional
Network | Localhost/staging; stable internet for Mailchimp/Mailgun sandbox
Data | Seed products/brands/categories/users; test emails
Logging | Server console logs; access to error logs if available

## TestPlan_Reporting
Topic | Details | Frequency | Audience | Format | Owner
Daily Test Progress | Tiến độ, Pass/Fail, Defects mới, Blockers | Daily | QA/Dev/PM | Email/Chat/Sheet | QA
Defect Reporting | Tạo/lưu lỗi theo mẫu (mô tả, steps, expected/actual, ảnh) và phân loại mức độ | Realtime | QA/Dev | Tracker/Sheet | QA
Weekly Summary | Phủ kiểm, xu hướng lỗi, rủi ro và hành động | Weekly | PM/Stakeholders | Slide/MD | QA
Final Test Report | Tỉ lệ pass, lỗi theo mức độ/trạng thái, quyết định release, bài học kinh nghiệm | At Exit | PM/Stakeholders | PDF/MD | QA
Metrics | Pass rate, Defect density, Coverage by module, Lead time fix | Daily/Final | QA/PM | Charts in report | QA
Communication | Kênh liên lạc & thời gian cập nhật (Email/Chat/Standup) | Daily | All | Schedule note | PM

## TestPlan_Resources
Role | Name/Team | Responsibilities
QA Engineer | <Your Name> | Test design/execution/reporting | evidence
Backend Reviewer | Server Dev | API behavior & defect triage
Frontend Reviewer | Client Dev | UI behavior & defect triage
Project Manager | PM | Plan approval | scheduling | risk handling

## TestPlan_Risks
Risk | Impact | Likelihood | Mitigation
Missing role checks (order status/review moderation) | High | Medium | Add negative tests; raise bugs; quick patches before release
Address endpoints missing auth on PUT/DELETE/GET | High | High | Restrict via middleware; add owner checks; test and track
Email provider sandbox limits | Low | Medium | Stub or verify only 200 responses; avoid SLA assumptions
Insufficient seed data for flows | Medium | Medium | Prepare deterministic seed; reset DB between runs
Performance regressions on listing/search | Medium | Low | Smoke test with pagination and limits; profile queries

## TestPlan_Schedule_Milestones
Milestone | Target Date | Owner | Notes
Approve Test Plan | 2025-12-16 | PM/Approver
Complete Test Design | 2025-12-18 | QA
Start Test Execution | 2025-12-18 | QA
Cycle 1 Bug Fix/Retest | 2025-12-19 | Dev/QA
Regression Pass | 2025-12-20 | QA
Exit Review & Sign-off | 2025-12-21 | PM/QA/Dev

## TestPlan_Scope_Strategy
Section | Item | Description
In-Scope | Authentication | Login, Register, Forgot/Reset, social callbacks
In-Scope | User Profile | /user/me view + update
In-Scope | Address | Add/list own addresses; ownership & auth checks
In-Scope | Catalog | Product list with filters (price, rating, category, brand) + sort
In-Scope | Search | /product/list/search/:name suggestions
In-Scope | Product Detail | /product/item/:slug data correctness
In-Scope | Wishlist | Add/Remove/list (auth, admin blocked)
In-Scope | Cart | Create cart, add/remove items, quantity rules, stock adjust
In-Scope | Checkout/Order | Submit order with address + payment method; view history/detail; complete/cancel rules
In-Scope | Reviews | Post only for Delivered/Completed items; moderation
In-Scope | Brand/Category | Active lists and select endpoints
In-Scope | Dashboard | Admin summary (/dashboard/summary)
In-Scope | Newsletter | /newsletter/subscribe
In-Scope | Contact | /contact/add
Out-of-Scope | Real Payment | Payment gateway integrations
Out-of-Scope | External Email SLA | Mail provider availability beyond sandbox
Out-of-Scope | Heavy Performance | Load/stress/volume beyond smoke
Out-of-Scope | Native Apps | Mobile native clients
Strategy | Functional | End-to-end flows on UI and responses
Strategy | API Integration | Verify status codes, payloads, DB side effects
Strategy | Security & Access | AuthN/AuthZ/roles; owner checks
Strategy | Regression | Smoke on catalog/search/cart/order each release
Strategy | Compatibility | Chrome/Firefox latest; Safari/Edge best-effort
Strategy | Performance (smoke) | Pagination & featured/popular limits
Stages | System Test | QA executes against staging/local
Stages | UAT | Optional stakeholder verification
Entry Criteria | Readiness | Env up, data seeded, plan approved, test design ≥95%
Exit Criteria | Quality Gates | No P0/P1 open; P2 planned; pass rate ≥95% on critical

## TestPlan_TestTypes
Type | Objective | Notes
Functional | Validate features behave as specified across key flows | UI + API checks
API Integration | Verify request/response codes, payloads and DB effects | Use Postman/REST client
Security & Access | Enforce authentication/authorization/ownership | Negative tests for missing role checks
Regression | Prevent re‑introduction of critical defects | Run smoke each release
Compatibility | Confirm basic operation on supported browsers | Chrome/Firefox latest
Performance (smoke) | Ensure listing/search/featured/popular handle nominal volume | Check pagination/limits

## TestPlan_Traceability
Area | Endpoint/Route | Key Test Criteria
Auth | /auth/login | 400 for missing fields; 400 for wrong email/pass; returns Bearer token; JWT payload contains id only
Auth | /auth/register | Unique email; hashed password; returns token; optional newsletter subscribe
Auth | /auth/forgot | /auth/reset | Reset token TTL; change password; login with new password
User | /user/me (auth) | Returns profile + role; update profile fields
User | /user (admin) | List with pagination; non‑admin blocked
Address | /address/add (auth) | Add for self; JWT required
Address | /address (auth) | List own addresses
Address | /address/:id PUT/DELETE | (BUG) missing auth/owner checks — negative tests
Product | /product/list | Filters (min/max/rating), sort fallback; category/brand filters
Product | /product/item/:slug | 404 if brand inactive/null; details correct
Product | /product/list/search/:name | 404 when none; safe for injection‑like inputs
Product | /product/featured | /product/popular | Respect limit and sort; active only
Cart | /cart/* (auth) | Purchaser gate blocks admin; create/update/delete; stock adjust
Order | /order/add (auth) | Payment method required; shipping required; address ownership
Order | /order/me | /order/:orderId | View history/detail; ownership enforced
Order | /order/complete/:orderId | Block admin; ensure all items delivered before complete
Order | /order/status/item/:itemId | (BUG) missing role‑check — negative test and defect
Wishlist | POST/GET (auth) | Admin blocked; duplicate prevent; bad product id
Review | /review/add | Only after Delivered/Completed; ownership and duplicates; approval default
Review | /review approve/reject/delete | (BUG) admin role‑check missing — negative tests
Newsletter | /newsletter/subscribe | Email required; duplicate handling
Contact | /contact/add | Required fields; duplicate email blocked
Brand/Category | /brand/list | /category/list | Active only; select endpoints
Dashboard | /dashboard/summary | Admin only; computed fields present
Health | /health | 200 OK